## Table
10.1 | Agreement between Gaylord National, LLC and Perini/Tompkins Joint Venture, dated as of May 9, 2005, relating to the construction of the Gaylord National, including certain amendments thereto (incorporated by reference to Exhibit 10.14 to the Companys Annual Report on Form 10-K for the year ended December 31, 2005, Exhibit 10.2 to the Companys Current Report on Form 8-K dated July 5, 2006, Exhibit 10.2 to the Companys Current Report on Form 8-K dated October 31, 2006, Exhibits 10.2, 10.3 and 10.4 to the Companys Current Report on Form 8-K dated April 18, 2007, Exhibit 10.2 to the Companys Current Report on Form 8-K dated May 11, 2007, Exhibit 10.2 to the Companys Current Report on Form 8-K dated June 26, 2007 and Exhibits 10.2, 10.3 and 10.4 to the Companys Current Report on Form 8-K dated February 7, 2008.
10.2 | Amendment Number 33 to the Agreement between Gaylord National, LLC and Perini/Tompkins Joint Venture, effective as of November 26, 2008.

## Table-1
10.1 | Agreement between Gaylord National, LLC and Perini/Tompkins Joint Venture, dated as of May 9, 2005, relating to the construction of the Gaylord National, including certain amendments thereto (incorporated by reference to Exhibit 10.14 to the Companys Annual Report on Form 10-K for the year ended December 31, 2005, Exhibit 10.2 to the Companys Current Report on Form 8-K dated July 5, 2006, Exhibit 10.2 to the Companys Current Report on Form 8-K dated October 31, 2006, Exhibits 10.2, 10.3 and 10.4 to the Companys Current Report on Form 8-K dated April 18, 2007, Exhibit 10.2 to the Companys Current Report on Form 8-K dated May 11, 2007, Exhibit 10.2 to the Companys Current Report on Form 8-K dated June 26, 2007 and Exhibits 10.2, 10.3 and 10.4 to the Companys Current Report on Form 8-K dated February 7, 2008.
10.2 | Amendment Number 33 to the Agreement between Gaylord National, LLC and Perini/Tompkins Joint Venture, effective as of November 26, 2008.
10.3 | First Amendment to Executive Employment Agreement, dated as of December 18, 2008, by and between the Company and Colin V. Reed.

## inter alia
inter alia,
Issue No. | Description | Date Published
Initial Guestroom Review
(Segment C  Floors 2-6 & 8)
1 | Punch List 1 | 8/16/2007
Initial Guestroom Review
(Segment C  Floors 6-10)
2 | Punch List 2 | 8/23/2007
Initial Guestroom Review
(Segment C  Floors 3 & 5-12)
3 | Punch List 3 | 8/31/2007
Initial Guestroom Review
(Segment C  Floor 1)
4 | Punch List 4 | 9/07/2007
Initial Guestroom Review
(Segment C  Floors 8, 9 & 12)
Completion Review No. 1
(Segment C  Floors 2-5)
5 | Punch List 5 | 9/14/2007
Initial Guestroom Review
(Segment D  Floors 2 & 3)
Completion Review No. 1
(Segment C  Floors 6-10)
Completion Review No. 2
(Segment C  Floor 2)
6 | Punch List 6 | 9/21/2007

## inter alia-1
Issue No. | Description | Date Published
Initial BOH Review
(Segments A/B  Floor 1)
Initial Guestroom Review
(Segment C  Floors 11 & 12)
(Segment D  Floor 3)
Completion Review No. 1
(Segment C  Floors 7-10)
Floors 1 & 7-12 include MEP comments
7 | Punch List 7 | 9/28/2007
Initial Guestroom Review
(Segment D  Floor 4)
8 | Punch List 8 | 10/5/2007
Initial BOH Review
(Segments A/B  Floor 1)
Initial Guestroom Review
(Segment D  Floors 5-7)
9 | Punch List 9 | 10/12/2007
Initial Guestroom Review
(Segment A  Floors 3 & 4)
Initial BOH Review
(Segment A/B  Floor 1)
Floor 1 includes MEP comments
10 | Punch List 10 | 10/19/2007
Initial BOH Review
(Segments A / B  Floor 1)
Initial Guestroom Review
(Segment B  Floor 3)
(Segments A/B  Floors 4 & 5)
(Segment A  Floor 6)
Floor 1 includes MEP comments
11 | Punch List 11 | 10/26/2007
Initial BOH Review
(Segment B  Floor 1)
Initial Guestroom Review
(Segments A / B  Floors 5-7)
12 | Punch List 12 | 11/2/2007
Initial BOH Review
(Segment B  Floor 1)
Initial Guestroom Review
(Segments A / B  Floors 7 & 8)
13 | Punch List 13 | 11/9/2007
Initial Guestroom Review
(Segments A / B  Floors 8 & 9)
14 | Punch List 14 | 11/16/2007

## inter alia-2
Issue No. | Description | Date Published
Initial Guestroom Review
(Segment B  Floors 4, 6 & 7)
(Segments A / B  Floors 8, 10 & 11)
15 | Punch List 15 | 11/21/2007
Initial Guestroom Review
(Segment E  Floor 3)
(Segments B & E  Floor 4)
(Segment A/B  Floor 11)
16 | Punch List 16 | 12/7/2007
Initial Guestroom Review
(Segment E  Floors 4 & 5)
(Segment B  Floor 7)
17 | Punch List 17 | 12/14/2007
Initial Guestroom Review
(Segment E  Floor 4)
(Segments A, A/B & E  Floor 5)
(Segment E  Floor 6)
18 | Punch List 18 | 12/21/2007
Initial Guestroom Review
(Segment A  Floors 4 & 12)
(Segment B  Floors 4, 8)
(Segment C  Floors 8, 9, 10 & 12)
(Segment D  Floors 4, 5 & 7)
(Segment E  Floors 3-6)
Floors 2 & 3 include MEP comments
19 | Punch List 19 | 1/4/2008
Initial Guestroom Review
(Segment A  Floors 9 & 12)
(Segment A/B  Floors 9 & 12)
(Segment B  Floors 9 & 10)
(Segment C  Floors 2, 3, 4, 5)
20 | Punch List 20 | 1/11/2008
Initial Guestroom Review
(Segment A  Floors 5, 6 & 11)
(Segment A/B  Floors 5, 6, 11 & 12)
(Segment B  Floors 5, 6, 7, 9 & 12)
(Segment C  Floor 6)
(Segment D  Floors 3, 4, 5 & 6)
(Segment E  Floors 3, 5, & 6)
21 | Punch List 21 | 1/18/2008
Initial Guestroom Review
(Segment A  Floors 7 & 14)
(Segment A/B  Floor 7)
(Segment B  Floors 6, 7, 11 & 12)
(Segment C  Floor 7)
22 | Punch List 22 | 1/25/2008

## inter alia-3
Issue No. | Description | Date Published
Initial Guestroom Review
(Segment A  Floors 3-10, 14 & 15)
(Segment A/B  Floors 6-10, 14 & 15)
(Segment B  Floors 4, 5, 8, 9, 14 & 15)
(Segment C  Floors 3, 5, 6, 9 & 10)
(Segment E  Floor 5 & 6)
Floors 3, 4, 5, 6, 7 & 8 include MEP comments
23 | Punch List 23 | 2/1/2008
Initial Guestroom Review
(Segment A  Floors 2, 6, 7, 8, 11, 12 & 16)
(Segment A/B  Floors 7, 8, 9, 11, 12, 15 & 16)
(Segment B  Floors 3, 7, 10, 11, 12, 15 & 16)
(Segment C  Floors 6, 7, 8 & 12)
(Segment D  Floors 3, 4, 5, 6 & 7)
(Segment E  Floor 5)
Floors 3, 4, 5, 6, 7 & 9 include MEP comments
24 | Punch List 24 | 2/11/2008
Initial Guestroom Review
(Segment A  Floors 7, 8, 9, 14, 15 & 17)
(Segment A/B  Floors 14, 15, 17 & 18)
(Segment B  Floors 5-11 & 14-18)
(Segment C  Floors 2, 3, 9, 10 & 11)
(Segment D  Floors 3 & 5)
(Segment E  Floors 4 & 5)
Floor 17 includes MEP comments
25 | Punch List 25 | 2/19/2008
Initial Guestroom Review
(Segment A  Floors 10, 11, 12, 15, 16 & 17)
(Segment A/B  Floors 5-18)
(Segment B  Floors 4, 9, 10, 12, 14, 16, 17 & 18)
(Segment C  Floors 3, 4, 7, 8, 9 & 12)
(Segment D  Floor 5)
Floors 5-17 include MEP comments
26 | Punch List 26 | 2/26/2008
Initial Guestroom Review
(Segment A  Floors 3-19)
(Segment A/B  Floors 4-12, 17 & 19)
(Segment B  Floors 3, 4, 10, 12 & 19)
(Segment C  Floors 1-12)
(Segment D  Floors 2, 3, 4 & 7)
(Segment E  Floors 3, 4 & 7)
Floors 4, 5, 6, 7, 8 & 9 include MEP comments
27 | Punch List 27 | 3/5/2008

## inter alia-4
Issue No. | Description | Date Published
Initial Guestroom Review
(Segment A  Floors 3, 5, 14 & 17)
(Segment A/B  Floors 10, 11, 12 & 14)
(Segment B  Floors 3, 5, 6, 8, 10, 11, 12 & 17)
(Segment D  Floors 2, 4, 5, 6 & 7)
(Segment E  Floors 3, 6 & 7)
28 | Punch List 28 | 3/13/2008
Initial Guestroom Review
(Segment A  Floors 6 & 15-17)
(Segment A/B  Floors 14-19)
(Segment B  Floors 14-19)
(Segment D  Floor 6)
(Segment E  Floor 6)
Initial Public Spaces Review
(Segment B  Floor 1)
(Segment D  Floors 0 & 1)
(Segment E  Floors 0 & 1)
29 | Punch List 29 | 3/19/2008
Initial Guestroom Review
(Segment A  Floors 7, 8 & 10)
(Segment B  Floors 4, 9 & 19)
(Segment E  Floor 7)
Initial Public Spaces Review
(Segment A  Floors 0, 1 & 2)
(Segment A/B  Floor 2)
(Segment C  Floor 1)
(Segment D  Floor 1)
(Segment E  Floor 1)
Initial Pool / Fitness Review
(Floor B1)
Floor B1 includes MEP comments
30 & 31 | Punch Lists 30 & 31 | 3/21/2008
Initial Public Spaces Review
(Segment A  Floors 0 & 2)
(Segment A/B  Floors 0 & 2)
(Segment B  Floor 1)
(Segment D  Floors 0 & 1)
(Segment E  Floors 1 & 2)
32 | Punch List 32 | 3/24/2008

## inter alia-5
Issue No. | Description | Date Published
Initial Public Spaces Review
(Segment A  Floor 2)
(Segment A/B  Floors 0 & 2)
(Segment B  Floors 0 & 1)
(Segment D  Floor 0)
Initial Guestroom Review
(Segment A  Floors 3-19)
(Segment A/B  Floors 12-19)
(Segment B  Floors 3-19)
Initial Pool / Fitness Review
(Floor B1)
33 | Punch List 33 | 3/28/2008
Initial Public Spaces Review
(Segment A  Floor 0)
(Segment A/B  Floors 0 & 2)
(Segment B  Floors 0 & 2)
(Segment D  Floor 0)
(Segment E  Floor 1)
Initial Guestroom Review
(Segment A  Floors 14 & 16-19)
(Segment A/B  Floors 5-11, 14, 15, 17 & 19)
(Segment B  Floors 3, 4, 7, 11 & 19)
(Segment D  Floor 7)
Initial Pool / Fitness Review
(Floor B1)
Floors 0 & B1 include MEP comments
34 | Punch List 34 | 4/8/2008
Initial Public Spaces Review
(Segment A  Floors 0-2)
(Segment A/B  Floors 0 & 2)
(Segment B  Floors 0-2)
(Segment D  Floors 0 & 1)
(Segment E  Floors 0-2)
Initial Guestroom Review
(Segment A  Floors 7 & 17)
(Segment A/B  Floors 5, 18 & 19)
(Segment B  Floors 3-7 & 10-19)
(Segment D  Floors 4, 6 & 7)
(Segment E  Floors 3-7)
Initial Pool / Fitness Review
(Floor B1)
Initial Penthouse Review
(Segments A, A/B, C & D)
Floors 1-3, 5-7, 18-19 & Penthouse include MEP comments
35 | Punch List 35 | 4/16/2008

## inter alia-6
Issue No. | Description | Date Published
Initial Guestroom Review
(Segment H  Floors 4 & 5)
1 | Punch List 1 | 2/8/2008
Initial Guestroom Review
(Segment H  Floors 5, 6 & 7)
2 | Punch List 2 | 2/15/2008
Initial Guestroom Review
(Segment H  Floors 6 & 7)
3 | Punch List 3 | 2/22/2008
Initial Guestroom Review
(Segment H  Floors 4, 5, 6, 7 & 8)
4 | Punch List 4 | 2/29/2008
Initial Guestroom Review
(Segment H  Floors 6, 7, 8, 9 & 10)
5 | Punch List 5 | 3/7/2008
Initial Meeting Rooms Review
(Segment H  Floor 2)
Initial Guestroom Review
(Segment H  Floors 6-11)
6 | Punch List 6 | 3/20/2008
Initial Public Spaces Review
(Segment H  Floor 2)
Initial Guestroom Review
(Segment H  Floors 5, 10, 11 & 12)
7 | Punch List 7 | 3/25/2008
Initial Guestroom Review
(Segment H  Floors 4-12)
8 | Punch List 8 | 4/2/2008
Initial Public Spaces Review
(Segment H  Floors 1 & 2)
Initial Guestroom Review
(Segment H  Floors 4-12)
Initial Penthouse Review
(Segment H) Floors 1, 2 & 4-12 include MEP comments
9 | Punch List 9 | 4/24/2008

## inter alia-7
Issue No. | Description | Date Published
Initial Review with MEP comments
Level 61  Convention Services (Floor 01)
1 | Punch List 1 | 10/2/2007
Initial Review
Level 38  Exhibition Hall (Floor 00)
Level 61  Kitchen / BOH (Floor 01)
2 | Punch List 2 | 10/9/2007
Completion Review No. 1
Level 61  Convention Services (Floor 01)
3 | Punch List 3 | 10/16/2007
Initial Review
Level 38  BOH (Floor 00)
Initial Review with MEP comments
Level 61  BOH (Floor 01)
4 | Punch List 4 | 10/19/2007
Initial Review
Level 38  BOH (Floor 00)
Initial Review with MEP comments
Level 61  BOH (Floor 01)
5 | Punch List 5 | 11/09/2007
Initial Review with Cini-Little Comments
Level 61  Room Service Kitchen & Employee Servery Kitchen
(Floor 01)
6 | Punch List 6 | 12/07/2007
Completion Review No. 1
Level 38  BOH (Floor 00)
7 | Punch List 7 | 12/21/2007
Initial Review
Level 38  Front of House (Floor 00)
Level 78  Engineering Offices (Floor 02)
8 | Punch List 8 | 01/07/2008
9 | Initial Review Level 38  Exhibition Hall (Floor 00) Level 78  Ballrooms & Meeting Rooms (Floor 02) Punch List 9 | 01/28/2008
Initial Review
Level 38  Prefunction Areas (Floor 00)
Level 78  Kitchen Areas (Floor 02)
10 | Punch List 10 | 02/15/2008

## inter alia-8
Issue No. | Description | Date Published
Initial Review
Level 78  Offices (Floor 02)
Level 86  Human Resources (Floor 03)
11 | Punch List 11 | 02/22/2008
Initial Review
Level 100  Control Rooms, Meeting Rooms & Spot Pods
(Floor 04)
12 | Punch List 12 | 02/29/2008
Initial Review
Level 78  Corridors & Storage Rooms (Floor 02)
Level 86  Human Resources (Floor 03)
Level 100  Corridors, Storage & Spot Pods (Floor 04) Stairs
13 | Punch List 13 | 3/17/2008
Initial Review
Level 38  Back of House (Floor 00)
Level 78  BOH / CUP (Floor 02)
Level 100  BOH / CUP (Floor 04) Stairs
14 | Punch List 14 | 3/25/2008
Initial Review
Level 38  Exhibit Hall & Public Spaces (Floor 00)
Level 61  Atrium (Floor 01)
Level 78  Public Spaces (Floor 02) Stairs
15 | Punch List 15 | 4/3/2008
Initial Review
Level 38  Corridors & Mech Rooms (Floor 00)
Level 61  Kitchen Areas, Corridors & Mechanical Rooms
(Floor 01)
Level 86  Mechanical Rooms (Floor 03)
Level 100  Mechanical Rooms (Floor 04)
Stairs
Floor 01 includes MEP comments
16 | Punch List 16 | 4/28/2008

## inter alia-9
Issue No. | Description [TO BE FURNISHED] | Date Published
4/15 &16/08,
Lighting & 6/2/08
| Initial AV and Technical Lighting Review | E-mail update;
| (Site  Convention Center) | 2/18/08 Audio-Video
| (Site  Hotel) | Systems; and
| (Site  Site) | 2/12/08 Stage
1 | Punch List 1 | Rigging

## witnesseth
WITNESSETH
GAYLORD ENTERTAINMENT COMPANY
| By: | /s/ Carter R. Todd
Carter R. Todd, Executive Vice President
EXECUTIVE
/s/ Colin V. Reed
Colin V. Reed